## Risk Calculation Sheet
CIBC — Digital Insurance Platform Acquisition ¦ Risk Calculation Sheet ¦ ALY6130 ¦ Group 7
Probability of Occurrence | Score
Very Unlikely | 1
Somewhat Unlikely | 3
50-50 Possibility | 5
Somewhat Likely | 7
Very Likely | 9
Impact of Risk | Score | Financial | Operational | Competitive | Reputational | Technical | Legal/Compliance
Very Low | 1 | Maintenance costs | Change management |  | Brand monitoring | Algorithm performance | Vendor compliance
Somewhat Low | 2 | Tech obsolescence costs | Limited human capital |  | System failure optics | Attack tolerance
Moderate | 4 | Vendor lock-in costs | Third-party tool dependency | Tech readiness & user experience |  | System scalability | Conflict with regulatory standards
Somewhat High | 6 | Litigation/compliance costs | Integration disruption | Competitor decision accuracy | Minimal human touch | Training data quality | Bias and discrimination costs
High | 8 | Efficiency cost savings | Data accuracy issues | Cost of lagging in tech adoption | Data privacy breaches | Algorithmic bias | Regulatory change adjustments
Extremely High | 9 | Initial capital costs | System failure/downtime | Global market competition | Ethical/fairness concerns | Limited training data | Compliance risk (privacy/security)
THRESHOLD DEFINITIONS
HIGH | Score 36–81 | Immediate Board escalation. Active mitigation plan within 30 days.
MEDIUM | Score 10–35 | Assigned owner. Monthly reporting. Mitigation plan within 60 days.
LOW | Score 1–9 | Accept with periodic review. Routine monitoring only.
POSITIVE | Any score | Exploit actively. Assign owner. Track realisation with KRI quarterly.

## Risk Register
CIBC — Risk Register ¦ ALY6130 ¦ Group 7 ¦ June 2026
Risk # | Risk Name | Type | Likelihood (X) | Impact (Y) | Risk Score (L×I) | Priority | Risk Owner | Status
1 | Data Privacy Breach | Negative | 9 | 8 | 72 | H | CISO / Chief Compliance Officer | Open
2 | Regulatory & Compliance Exposure | Negative | 7 | 8 | 56 | H | Chief Compliance Officer | Open
3 | First-Mover Market Capture | Positive | 7 | 8 | 56 | H | Chief Strategy Officer / CFO | Open
4 | AI Underwriting Bias | Negative | 7 | 8 | 56 | H | Chief Risk Officer / CDO | Open
14 | Cross-Sell Revenue Uplift | Positive | 7 | 8 | 56 | H | Chief Revenue Officer | Open
28 | Wealth Mgmt Referral Uplift | Positive | 7 | 8 | 56 | H | Chief Wealth Management Officer | Open
30 | Platform Reusability Blueprint | Positive | 7 | 8 | 56 | H | Chief Strategy Officer / CTO | Open
11 | Advisor Channel Failure | Negative | 7 | 7 | 49 | H | Chief Distribution Officer | Open
17 | Adverse Selection / Pricing | Negative | 7 | 7 | 49 | H | Chief Actuarial Officer / CRO | Open
20 | Provincial Reg. Fragmentation | Negative | 7 | 7 | 49 | H | Chief Compliance Officer | Open
6 | Competitor Pre-emption | Negative | 5 | 9 | 45 | H | Chief Strategy Officer / CEO | Open
10 | Health Data Privacy Breach | Negative | 5 | 9 | 45 | H | Chief Privacy Officer / CISO | Open
16 | Dual Infrastructure Outage | Negative | 5 | 9 | 45 | H | CTO / COO | Open
21 | Ransomware Attack on Platform | Negative | 5 | 9 | 45 | H | CISO / CTO | Open
9 | Third-Party Vendor Lock-In | Negative | 7 | 6 | 42 | H | Chief Procurement Officer / CTO | Open
5 | Platform Integration Failure | Negative | 5 | 8 | 40 | H | CTO / COO | Open
12 | Claims Dispute / Brand Damage | Negative | 5 | 8 | 40 | H | Chief Client Officer | Open
15 | Data Intelligence Advantage | Positive | 5 | 8 | 40 | H | Chief Data Officer | Open
27 | Climate Claims Concentration | Positive | 5 | 8 | 40 | H | Chief Actuary / CRO | Open
7 | Client Adoption Shortfall | Negative | 5 | 7 | 35 | M | Chief Marketing Officer | Open
13 | Post-Acq. Cultural Failure | Negative | 5 | 7 | 35 | M | CHRO / Chief Strategy Officer | Open
23 | Interest Rate / ALM Risk | Negative | 5 | 7 | 35 | M | CFO / Chief Actuary | Open
25 | Negative Media at Launch | Negative | 5 | 7 | 35 | M | CCO / Chief Marketing Officer | Open
29 | Insurance-Mortgage Underwriting | Positive | 5 | 7 | 35 | M | Chief Data Officer / CRO | Open
8 | Integration Talent Loss | Negative | 5 | 6 | 30 | M | CHRO / CTO | Open
22 | Complaint Handling Failure | Negative | 5 | 6 | 30 | M | Chief Client Officer | Open
26 | Poor Mobile App UX | Negative | 5 | 6 | 30 | M | Chief Digital Officer / CTO | Open
18 | Money Laundering via Insurance | Negative | 3 | 9 | 27 | M | Chief Compliance Officer / CAMLO | Open
24 | OSFI Capital Adequacy Shortfall | Negative | 3 | 9 | 27 | M | CFO / CRO | Open
19 | Reinsurance Counterparty Failure | Negative | 3 | 8 | 24 | M | Chief Risk Officer / Chief Actuary | Open

## Scatter Risk Map
CIBC — Scatter Risk Map ¦ X-axis = Likelihood ¦ Y-axis = Impact ¦ ALY6130 ¦ Group 7 ¦ June 2026
X-axis = Likelihood (1=Very Unlikely ¦ 3=Somewhat Unlikely ¦ 5=50-50 ¦ 7=Somewhat Likely ¦ 9=Very Likely) ¦ Y-axis = Impact (1=Very Low ¦ 2=Somewhat Low ¦ 4=Moderate ¦ 6=Somewhat High ¦ 8=High ¦ 9=Extremely High) ¦ Risk Score = Likelihood × Impact
HIGH RISKS — RED (Score ≥ 36)
Risk # | Likelihood (X) | Impact (Y) | Risk Score
1 | 9 | 8 | 72
2 | 7 | 8 | 56
4 | 7 | 8 | 56
5 | 5 | 8 | 40
6 | 5 | 9 | 45
9 | 7 | 6 | 42
10 | 5 | 9 | 45
11 | 7 | 7 | 49
12 | 5 | 8 | 40
16 | 5 | 9 | 45
17 | 7 | 7 | 49
20 | 7 | 7 | 49
21 | 5 | 9 | 45
MEDIUM RISKS — YELLOW (Score 10–35)
Risk # | Likelihood (X) | Impact (Y) | Risk Score
7 | 5 | 7 | 35
8 | 5 | 6 | 30
13 | 5 | 7 | 35
18 | 3 | 9 | 27
19 | 3 | 8 | 24
22 | 5 | 6 | 30
23 | 5 | 7 | 35
24 | 3 | 9 | 27
25 | 5 | 7 | 35
26 | 5 | 6 | 30
POSITIVE RISKS — BLUE
Risk # | Likelihood (X) | Impact (Y) | Risk Score
3 | 7 | 8 | 56
14 | 7 | 8 | 56
15 | 5 | 8 | 40
27 | 5 | 8 | 40
28 | 7 | 8 | 56
29 | 5 | 7 | 35
30 | 7 | 8 | 56
THRESHOLD DOCUMENTATION
HIGH | Score ≥ 36 | X=Likelihood Y=Impact
MEDIUM | Score 10–35 | X=Likelihood Y=Impact
LOW | Score 1–9 | X=Likelihood Y=Impact
POSITIVE | Any score | X=Likelihood Y=Impact

## Heat Map Grid
CIBC — Risk Heat Map Grid ¦ Impact (rows) × Likelihood (columns) ¦ ALY6130 ¦ Group 7 ¦ June 2026
Impact ↓ / Likelihood → | 1 (Very Unlikely) | 3 (Somewhat Unlikely) | 5 (50-50) | 7 (Somewhat Likely) | 9 (Very Likely)
9 — Extremely High | 9 | Score = 27 R18 R24 | Score = 45 R6 R10 R16 R21 | 63 | 81
8 — High | 8 | Score = 24 R19 | Score = 40 R5 R12 R15+ R27+ | Score = 56 R2 R3+ R4 R14+ R28+ R30+ | Score = 72 R1
6 — Somewhat High | 6 | 18 | Score = 30 R8 R22 R26 | Score = 42 R9 | 54
4 — Moderate | 4 | 12 | 20 | 28 | 36
2 — Somewhat Low | 2 | 6 | 10 | 14 | 18
1 — Very Low | 1 | 3 | 5 | 7 | 9
← LIKELIHOOD (X-axis) →
HIGH — Risk Score ≥ 36 (Red)
MEDIUM — Risk Score 10–35 (Yellow)
LOW — Risk Score 1–9 (Green)
POSITIVE RISK — Opportunity (Blue)
Source: Group 7 Risk Register and Risk Calculation Sheet, ALY6130, Spring 2026.