## Risk Register
CIBC — Digital Insurance Platform Acquisition ¦ ALY6130 ¦ Group 7 ¦ Risk Register
Risk # | Date | The Risk of / That | Caused By | Resulting In | Consequence / Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation / Controls | Risk Owner | Open / Closed
1 | June 2026 | A data privacy breach exposing combined banking and insurance client records | Inadequate security controls and access management during the integration of a cloud-native insurance platform into CIBC's core banking infrastructure, creating a high-value combined data environment targeted by sophisticated threat actors | Mandatory breach notification obligations under PIPEDA, regulatory fines under Bill C-27, client trust erosion, and sustained reputational damage in a product category CIBC has just entered | Financial: Fines under PIPEDA/Bill C-27 could reach CAD $25M+; class-action costs could exceed CAD $50M. Operational: Mandatory audit and platform shutdown could delay launch 6–12 months. Legal/Compliance: OSFI may require suspension of insurance product sales. Reputational: Client churn across banking and insurance lines; years of brand recovery investment required. | 9 | 8 | 72 | H | Zero-trust architecture; end-to-end encryption; Privacy Impact Assessment pre-launch; 24/7 CISO-led Security Operations Centre; mandatory breach notification procedures | CISO / Chief Compliance Officer | Open
2 | June 2026 | Regulatory non-compliance with provincial insurance licensing rules and federal data privacy legislation | The rapidly evolving regulatory landscape governing digital insurance distribution, AI-assisted underwriting decisions, and personal health data privacy under PIPEDA and the forthcoming Bill C-27, combined with CIBC's limited prior experience operating in the provincially regulated insurance sector | Regulatory fines, mandatory product withdrawal from non-compliant provinces, forced system modifications to the insurance platform, and reputational harm from public regulatory action | Financial: Fines could reach CAD $10M per incident; premium refunds CAD $5–20M. Operational: Regulatory halt could delay operations 3–9 months. Legal/Compliance: OSFI may impose enhanced oversight on CIBC's banking licence. Reputational: Public enforcement generates national media coverage, eroding client trust. | 7 | 8 | 56 | H | Dedicated compliance officer on project team; automated regulatory monitoring; provincial licensing review before each province launch; board-approved compliance roadmap; quarterly legal reviews | Chief Compliance Officer | Open
3 | June 2026 | Capturing significant first-mover advantage in the Canadian digital banking-and-insurance integration market | CIBC's early entry into integrated digital insurance distribution leveraging its existing base of 11 million banking clients and trusted brand, ahead of insurtech competitors like Lemonade and PolicyMe and rival Canadian banks that have not yet launched equivalent integrated platforms | Substantial digital insurance market share gain, increased revenue per household, deeper and more durable client relationships, and a sustainable competitive advantage difficult for pure insurtechs or rival banks to replicate | Financial (positive): 5% adoption among 11M clients within 18 months ≈ CAD $165M annual premiums. Strategic (positive): Bundled clients have 60% lower attrition than single-product clients. Competitive (positive): Brand differentiation insurtechs cannot replicate without banking licences. Opportunity cost if missed: CAD $40–60M in extra marketing spend to catch up 3–4 years later. | 7 | 8 | 56 | H | Accelerate go-live as board-level strategic priority; dedicated digital insurance marketing budget; advisor cross-sell incentive programme; protect platform quality to avoid reputational risk at launch | Chief Strategy Officer / CFO | Open
Risk Score = Likelihood Score × Impact Score ¦ High (H) = 36–81 ¦ Moderate (M) = 10–35 ¦ Low (L) = 1–9 ¦ Shaded green rows = Positive Risks (opportunities to exploit) | [12 empty] | * see KRI sheet for thresholds

## Problem Statements
CIBC — Problem Statements (SWOT → Risk Translation) ¦ Group 7
Risk # | Risk Name | SWOT Source | Problem Statement
1 | Data Privacy Breach (Negative) | THREAT: Combined banking and insurance data creates a high-value cyberattack target at a scale CIBC has not previously faced. | Insurtech competitors have highlighted the dangers of combined financial and insurance data environments — Lemonade experienced a data breach in 2022 affecting policyholder records. CIBC is now building exactly this type of combined environment. The risk requires immediate monitoring because the integration window is the period of greatest vulnerability, PIPEDA and Bill C-27 impose strict breach notification obligations, and a breach during or immediately after launch would cause regulatory penalties and permanent reputational damage in a market CIBC has not yet established itself.
2 | Regulatory & Compliance Exposure (Negative) | THREAT: The regulatory landscape around digital insurance, data privacy (PIPEDA, Bill C-27), and consumer protection is shifting quickly. | Canada's federal government tabled Bill C-27 in 2023, which will significantly strengthen PIPEDA obligations and introduce AI transparency requirements relevant to CIBC's planned AI-assisted underwriting processes. Provincial insurance regulators across Ontario, Quebec, and British Columbia have issued updated digital distribution guidelines. Regulatory delays or a compliance-driven product halt could allow competitors such as Lemonade and PolicyMe to accelerate Canadian market penetration while CIBC is sidelined.
3 | First-Mover Market Capture (Positive) | OPPORTUNITY: Canada's digital insurance market is growing fast, and an early move by a trusted bank brand like CIBC could carve out a meaningful competitive position. | McKinsey (2023) indicates Canadian consumers are significantly more willing to purchase insurance from their primary bank than from a standalone insurtech. PolicyMe reported 40% YoY premium growth in 2023. TD and RBC have announced digital insurance partnerships but have not yet launched integrated products, giving CIBC a narrow window to establish first-mover advantage. If CIBC executes well and captures early adopters, those clients are highly unlikely to switch — creating a durable revenue stream.

## KRI Framework
CIBC — Key Risk Indicator (KRI) Framework — Traffic Light Thresholds ¦ Group 7
Risk # | KRI (Leading Indicator) | GREEN — Optimized (Within Risk Appetite) | AMBER — Warning (Risk Increasing) | RED — Critical (Immediate Action) | KRI Owner
1 | No. of critical security vulnerabilities unpatched beyond 72 hours | Zero critical vulnerabilities unpatched >72 hrs. Security posture is within CIBC's defined risk appetite. | 1 critical vulnerability unpatched >72 hrs. Integration security team notified. Patch timeline escalated to CISO. Weekly reporting to senior leadership begins. | 2+ unpatched critical vulnerabilities >72 hrs OR any confirmed unauthorised access attempt. Immediate CISO escalation to CEO and Board. Platform integration paused pending security audit. | CISO
2 | No. of open compliance findings or unimplemented regulatory changes older than 30 days | Zero open findings >30 days. All provincial licensing requirements confirmed complete before launch in each province. | 1–2 open findings >30 days. Compliance committee convened. Remediation timeline approved by Chief Compliance Officer. Monthly board reporting begins. | 3+ open findings unresolved >30 days OR a formal regulatory inquiry received from any provincial insurance regulator or the Privacy Commissioner of Canada. Immediate escalation to CEO and Board. Platform sales halted in affected province(s). | Chief Compliance Officer
3 | Monthly digital insurance client adoption rate (% of active CIBC digital banking clients with at least one policy) | Adoption rate above 5% of active digital banking clients within 12 months of launch. Platform is capturing early market share ahead of projections. | Adoption rate 2–5% at 12 months post-launch. Marketing effectiveness reviewed. Advisor cross-sell incentive programme reassessed. Competitive benchmarking commissioned. | Adoption rate below 2% at 12 months post-launch OR a major Canadian bank competitor launches an integrated banking-and-insurance platform before CIBC achieves meaningful market share. Immediate strategy committee review. CEO briefed. | Chief Strategy Officer
Note: Red threshold for Risk 3 (positive) = opportunity window closing

## Risk Calculation Sheet
CIBC — Risk Calculation Sheet ¦ ALY6130 ¦ Group 7
Probability of Occurrence | Score
Very Unlikely | 1
Somewhat Unlikely | 3
50-50 Possibility | 5
Somewhat Likely | 7
Very Likely | 9
Impact Level | Score | Financial | Operational | Competitive | Reputational | Technical | Legal/Compliance
Very Low | 1 | Maintenance costs | Change management |  | Brand monitoring | Algorithm performance | Vendor compliance
Somewhat Low | 2 | Tech obsolescence costs | Limited human capital |  | System failure optics | Attack tolerance
Moderate | 4 | Vendor lock-in costs | Third-party tool dependency | Tech readiness & user experience |  | System scalability | Conflict with regulatory standards
Somewhat High | 6 | Litigation/compliance costs | Integration disruption | Competitor decision accuracy | Minimal human touch | Training data quality | Bias and discrimination costs
High | 8 | Efficiency cost savings | Data accuracy issues | Cost of lagging in tech adoption | Data privacy breaches | Algorithmic bias | Regulatory change adjustments
Extremely High | 9 | Initial capital costs | System failure/downtime | Global market competition from rivals | Ethical/fairness concerns | Limited training data | Compliance risk (privacy/security)
Risk 1 — Data Privacy Breach ¦ Negative Risk
Likelihood | Very Likely | Likelihood Score | 9 | Impact Score | 9 | Risk Score = 9 × 9 = 81 ¦ Priority: H
The risk of... | A data privacy breach exposing combined banking and insurance client records
Caused by... | Inadequate security controls during integration of cloud-native insurance platform into CIBC's core banking infrastructure
Resulting in... | Mandatory breach notification under PIPEDA, regulatory fines under Bill C-27, client trust erosion, and reputational damage
Impact of Risk | Financial | Operational | Competitive | Reputational | Technical | Legal/Compliance | Score Used
9 (Extremely High) | 9 | 8 | 8 | 9 | 8 | 9 | 9
Impact Statement | Financial: CAD $25M+ fines; $50M+ class-action exposure. Operational: 6–12 month launch delay. Legal/Compliance: OSFI may suspend insurance product sales. Reputational: Client churn across banking and insurance lines.
Mitigation / Controls | Zero-trust architecture; end-to-end encryption; Privacy Impact Assessment; 24/7 CISO-led SOC; breach notification procedures |  |  |  |  | Risk Owner | CISO / Chief Compliance Officer
Risk 2 — Regulatory and Compliance Exposure ¦ Negative Risk
Likelihood | Somewhat Likely | Likelihood Score | 7 | Impact Score | 8 | Risk Score = 7 × 8 = 56 ¦ Priority: H
The risk of... | Regulatory non-compliance with provincial insurance licensing rules and federal data privacy legislation
Caused by... | Rapidly evolving PIPEDA/Bill C-27 rules and CIBC's limited experience in the provincially regulated insurance sector
Resulting in... | Regulatory fines, mandatory product withdrawal, forced platform modifications, reputational harm from public enforcement
Impact of Risk | Financial | Operational | Competitive | Reputational | Technical | Legal/Compliance | Score Used
8 (High) | 9 | 8 | 8 | 8 | 6 | 9 | 8
Impact Statement | Financial: CAD $10M+ fines per incident; $5–20M premium refunds. Operational: 3–9 month regulatory halt. Legal/Compliance: OSFI enhanced oversight risk. Reputational: National media coverage erodes trust.
Mitigation / Controls | Dedicated compliance officer on project team; automated regulatory monitoring; provincial licensing reviews; board-approved compliance roadmap |  |  |  |  | Risk Owner | Chief Compliance Officer
Risk 3 — First-Mover Market Capture ¦ Positive Risk
Likelihood | Somewhat Likely | Likelihood Score | 7 | Impact Score | 8 | Risk Score = 7 × 8 = 56 ¦ Priority: H
The risk of... | Capturing significant first-mover advantage in Canada's digital banking-and-insurance integration market
Caused by... | CIBC's early entry leveraging 11M banking clients and trusted brand, ahead of insurtechs and rival banks not yet launched
Resulting in... | Digital insurance market share gain, increased revenue per household, durable client relationships, and sustainable competitive advantage
Impact of Risk | Financial | Operational | Competitive | Reputational | Technical | Legal/Compliance | Score Used
8 (High) | 9 | 6 | 9 | 8 | 6 | 4 | 8
Impact Statement | Financial (positive): ~CAD $165M annual premiums at 5% adoption. Strategic (positive): 60% lower attrition for bundled clients. Competitive (positive): Differentiation insurtechs cannot replicate. Opportunity cost if missed: CAD $40–60M extra marketing spend.
Mitigation / Controls | Accelerate go-live as board priority; dedicated marketing budget; advisor cross-sell incentives; protect platform quality pre-launch |  |  |  |  | Risk Owner | Chief Strategy Officer / CFO