## RT&RP — Module 4 Update
CIBC — Digital Insurance Platform Acquisition
Module 4 — Risk Treatment & Response Plan (RT&RP): Quantitative Assessment Update
ALY6130 — Risk Management Analytics ¦ Group 7: Ottun Oluwatomi • Efemena Okpa • Anthony Onwuka ¦ June 2026
Risk ID | Risk Name | Type | Module 3 Risk Score (L × I) | Quantitative Method Applied | Key Quantitative Output | Updated Treatment / Response Action | Primary I&W Monitoring Indicator | Warning Thresholds (GREEN / AMBER / RED)
R1 | Data Privacy Breach | Negative — Threat | L=9 × I=8 Score = 72 Priority: HIGH | Monte Carlo Simulation (Triangular Distribution 10,000 iterations) | Mean Expected Loss: CAD $82.8M 50th Percentile: CAD $81.0M 90th Percentile: CAD $118.7M ← Reserve 95th Percentile: CAD $127.8M ← Board Stress P(Loss > CAD $100M): 25.6% | 1. Set contingency reserve at CAD $119M (90th pct) 2. Board stress-test benchmark: CAD $128M (95th pct) 3. Deploy zero-trust network architecture pre-launch 4. Complete Privacy Impact Assessment before go-live 5. Stand up 24/7 SOC monitoring across integrated env. 6. Run Isolation Forest ML anomaly detection on SOC alerts 7. Annual penetration testing + bi-annual vuln. assessments | No. of critical security vulnerabilities unpatched beyond 72 hours Secondary: SOC anomalous- access alert volume; integration scan pass rate | GREEN: Zero unpatched >72 hrs. No escalation. AMBER: 1 unpatched >72 hrs — CISO notified; weekly senior leadership reporting begins. RED: 2+ unpatched OR confirmed unauthorised access — CEO/Board escalation; integration paused; incident response team activated.
R2 | Regulatory & Compliance Exposure | Negative — Threat | L=7 × I=8 Score = 56 Priority: HIGH | Sensitivity Analysis (Tornado Chart) 5 key drivers ±30% | Base Impact: CAD $56M Top Driver: Likelihood of Regulatory Halt Swing: ±CAD $11.8M (highest) 2nd Driver: Regulatory Fine Severity Swing: ±CAD $7.7M 3rd Driver: Provincial Launch Delay Duration Swing: ±CAD $6.3M | 1. Direct primary monitoring resources to compliance findings KRI — highest-sensitivity variable 2. Appoint dedicated compliance officer immediately 3. Deploy automated regulatory monitoring tools 4. Prioritise provincial licensing across all 10 provinces 5. Quarterly legal reviews of PIPEDA/Bill C-27 obligations 6. Train gradient boosting classifier on regulatory enforcement data for halt probability scoring 7. All open findings must clear within 30-day SLA | No. of open compliance findings or unimplemented regulatory changes beyond 30 days Secondary: Provinces with confirmed licence; days to Bill C-27 readiness | GREEN: Zero open findings >30 days; licences on schedule. No escalation required. AMBER: 1–2 open findings >30 days — compliance committee convened; monthly board reporting begins. RED: 3+ findings unresolved OR formal regulatory inquiry received — CEO/Board escalation; platform sales halted in affected provinces.
R3 | First-Mover Market Capture | Positive — Opportunity | L=7 × I=8 Score = 56 Priority: HIGH (+) | Expected Monetary Value (EMV Analysis) 4 adoption scenarios EMV = P × Net Value | Total EMV: CAD $187.1M Strong First-Mover (P=70%): CAD $168.0M Partial First-Mover (P=15%): CAD $17.8M Late Entry (P=10%): CAD $3.0M Failed Launch (P=5%): −CAD $1.8M Amber breach → −CAD $150M value Red breach → −CAD $165M value | 1. Pursue opportunity ACTIVELY — CAD $187.1M EMV justifies full resource investment 2. Assign Chief Strategy Officer as risk owner 3. Complete advisor provincial licensing within 6 months 4. Set 5% adoption at 12 months as primary success KRI 5. Monitor TD/RBC launch announcements weekly 6. Deploy LSTM time-series model forecasting monthly adoption from digital banking engagement data 7. Amber warning triggers emergency marketing review 8. Red warning triggers CEO/Board strategy reset | Monthly digital insurance client adoption rate (% of active CIBC digital banking clients) Secondary: TD/RBC confirmed launch date; advisor licensing % | GREEN: Adoption >5% at 12 months; no confirmed competitor launch. On track. AMBER: Adoption 2–5% at 12 months OR TD/RBC announces firm go-live within 6 months — emergency marketing review activated. RED: Adoption <2% at 12 months OR TD/RBC launches before CIBC achieves meaningful share — immediate CEO/Board strategy reset.
Sources: Group 7 Risk Register, Module 3 & 4 Submissions, ALY6130, Spring 2026 ¦ Monte Carlo: 10,000 iterations, triangular distribution ¦ EMV = Probability × Net Value ¦ Sensitivity: ±30% variation per driver ¦ I&W thresholds aligned with COSO (2010) KRI framework and NIST SP 800-30 Rev. 1 (2012)